## Adoption Activities
IG | Name | Description | Changes | Communication | Training | Support | Other
Group 1 | Customer Support Team | 250 in Orlando FL and 375 in San Jose CA call centers. Responsible for first line customer support. | New call center software in both call centers to go live in six months' time. Changes to job role description and to shift patterns to occur at the same time | Immediate: Inform team leaders of the upcoming change, for them to propogate to their team members. 3 months prior: Formal communication via email and letter to every team member, detailing the change and explaining why it is happening, what their role will be and what they can expect in terms of changes to job role, shift patterns etc, when the change will occur, and what training, support and incentives they will receive. Immediately after the letter: Series of voluntary meetings with management team and HR in attanedance to review the upcoming changes and answer any questions. 2 months prior: Email setting out training and go live dates and times for each cohort. 1 month prior: reminder emails. 1 week prior: reminder emails | Overview of changes, overview of new processes, overview of new software, detailed training on new software features and functions, detailed training on new processes, live simulation training exercises, testing on new software and processes, awareness of support availability, sign off by team manager | Initial support from line manager/team leader and from designated power users. First line support from the IT Tech Support Team, to go live contemporaneously with the new software. Second and third line support backed off to vendor as a managed service | Incentives will include a small bonus at the end of Month 1 for all users who have completed the training and been signed off as competent by their team leader
Group 2
Group 3
Group 4
Group 5
Group 6
Group 7
Group 8
Group 9
Group 10