## Activity List
Item | Description
Have all project outcomes been clearly defined and agreed? | Are all of the outcome requirements uncovered, and are they documented in terms of quality, quantity and deadline? Are all key stakeholders aware of these outcome requirements? Are they listed in priority order? Have major milestones en route to outcome atainment been identified and documented?
Have all processes that will undergo change been identified? | Are all of the level 3 (ie detailed) business capabilities that will be directly or indirectly impacted by the initiative correctly identified and documented (ie including new capabilities, changes to existing capabilities and retired capabilities)? Are all of the processes from these capabilities that will be directly or indirectly impacted by the initiative correctly identified and documented?
Has the nature of each process change been accurately documented? | For each process that will be directly or indirectly impacted (ie both new processes and existing processes that will undergo change), have the steps and activities within that process been correctly and accurately documented, with changes specifically noted?
Have all impacted users been identified? | For each directly or indirectly impacted process, are all the users of that process correctly identified and documented? Does this include numbers of users at each location?
Have impacted users been correctly assigned into IGs (impacted user groups)? | Have IGs (impacted groups) been created to simplify the management of adoption requirements amongst users and have users with the same activity and adoption needs been correctly assigned into these IGs?
Have the KSA needs of each IG been assessed and documented? | Have the adoption needs for each IG been accurately and completely assessed and documented, including there current and required knowledge, skills and attitude?
Have appropriate requirements for communication, training and support been identified for each IG? | Have decisions been made as to what communication, training and support will be need to provided for each IG to ensure that their KSA requirements are fully met, and have these been accurately documented?
Have all activities to deliver these requirements been selected, costed and approved? | Have decisions been made as to how this communication, training and support will be delivered, in terms of what activities need to happen, who will be responsible for these activities and how they will be funded?
Have appropriate ways for measuring the results of these activities been identified? | Have one or measurements been selected for each activity that will enable the activities' results to be measured?
Item | Description
Have all activities been assigned into project phases? | Have all the activities been prioritised or otherwise ordered into a logical sequence, and where necessary divided into multiple phases for delivery over time?
Have all assets and/or resources needed for the performance of these activities been created and/or assigned (if team members are global, consider time zone constraints)? | What assets and/or resources will be needed for each activity? Have these been acquired and if not how and when will they be acquired? Who will be responsible for ensuring they are in place and ready for use?
Have all mechanisms for delivery of activities (including third parties) been identified and made ready? | Who will actually perform the activities, and have they been notified of this? Do those who are involved require any training or coaching and has this been provided? Are there any other readiness considerations for those who will be involved in adoption delivery?
Have all activities (or at least those in upcoming phases) been scheduled as necessary? | Is there a detailed schedule for all activities within the upcoming phase or phases of the adoption plan, and is this published in a location and format that makes it easily accessible for all those who need to view it?
Have all necessary communications occurred? | Is everyone involved in the adoption delivery aware of the adoption schedule and of their own role within it? Have all necessary communications to impacted users taken place?
Have all necessary validations and approvals occurred? | Has sign-off been provided for any budget spend or release of users for training, etc? Has this been fully documented? Are all managers and team leaders aware of any time away from their primary tasks that the adoption plans will impose upon their department or team members, and has their agreement to this been secured?
Have all adoption barriers or challenges been addressed? | Have all adoption barriers and other challenges been accurately identified and dealt with? For those that remain, are there plans in place for dealing with them at the appropriate time, and have people and other resources been allocated to these plans as appropriate?
Have all potential risks been identified and plans for mitigation should they occurred been created? | Has a risk assessment taken place and have all risks been identified and then assessed for both likelihood of occurrence and level of impact? Have these risks then been prioritised and those with a medium or high priority been appropriately planned for in terms of either avoidance or of dealing with them when they occur? Is everyone who needs to know these plans aware of them?
Is there anything else that has not been done that needs to be done prior to project launch? | What else needs to be done that has not yet been done? Have you run through this list with others to ensure it is complete?
Are we ready to go? | Has a final check taken place to once again ensure everything is ready and in place?

## Phase 1
| Yes / No | Date | Comments
Have all project outcomes been clearly defined and agreed?
Have all processes that will undergo change been identified?
Has the nature of each process change been accurately documented?
Have all impacted users been identified?
Have impacted users been correctly assigned into IGs (impacted user groups)?
Have the KSA needs of each IG been assessed and documented?
Have appropriate requirements for communication, training and support been identified for each IG?
Have all activities to deliver these requirements been selected, costed and approved?
Have appropriate ways for measuring the results of these activities been identified?
Have all activities been assigned into project phases?
Have all assets and/or resources needed for the performance of these activities been created and/or assigned (if team members are global, consider time zone constraints)?
Have all mechanisms for delivery of activities (including third parties) been identified and made ready?
Have all activities (or at least those in upcoming phases) been scheduled as necessary?
Have all necessary communications occurred?
Have all necessary validations and approvals occurred?
Have all adoption barriers or challenges been addressed?
Have all potential risks been identified and plans for mitigation should they occurred been created?
Is there anything else that has not been done that needs to be done prior to project launch?
Are we ready to go?

## Phase 2
| Yes / No | Date | Comments
Have all project outcomes been clearly defined and agreed?
Have all processes that will undergo change been identified?
Has the nature of each process change been accurately documented?
Have all impacted users been identified?
Have impacted users been correctly assigned into IGs (impacted user groups)?
Have the KSA needs of each IG been assessed and documented?
Have appropriate requirements for communication, training and support been identified for each IG?
Have all activities to deliver these requirements been selected, costed and approved?
Have appropriate ways for measuring the results of these activities been identified?
Have all activities been assigned into project phases?
Have all assets and/or resources needed for the performance of these activities been created and/or assigned (if team members are global, consider time zone constraints)?
Have all mechanisms for delivery of activities (including third parties) been identified and made ready?
Have all activities (or at least those in upcoming phases) been scheduled as necessary?
Have all necessary communications occurred?
Have all necessary validations and approvals occurred?
Have all adoption barriers or challenges been addressed?
Have all potential risks been identified and plans for mitigation should they occurred been created?
Is there anything else that has not been done that needs to be done prior to project launch?
Are we ready to go?

## Phase 3
| Yes / No | Date | Comments
Have all project outcomes been clearly defined and agreed?
Have all processes that will undergo change been identified?
Has the nature of each process change been accurately documented?
Have all impacted users been identified?
Have impacted users been correctly assigned into IGs (impacted user groups)?
Have the KSA needs of each IG been assessed and documented?
Have appropriate requirements for communication, training and support been identified for each IG?
Have all activities to deliver these requirements been selected, costed and approved?
Have appropriate ways for measuring the results of these activities been identified?
Have all activities been assigned into project phases?
Have all assets and/or resources needed for the performance of these activities been created and/or assigned (if team members are global, consider time zone constraints)?
Have all mechanisms for delivery of activities (including third parties) been identified and made ready?
Have all activities (or at least those in upcoming phases) been scheduled as necessary?
Have all necessary communications occurred?
Have all necessary validations and approvals occurred?
Have all adoption barriers or challenges been addressed?
Have all potential risks been identified and plans for mitigation should they occurred been created?
Is there anything else that has not been done that needs to be done prior to project launch?
Are we ready to go?

## Phase 4
| Yes / No | Date | Comments
Have all project outcomes been clearly defined and agreed?
Have all processes that will undergo change been identified?
Has the nature of each process change been accurately documented?
Have all impacted users been identified?
Have impacted users been correctly assigned into IGs (impacted user groups)?
Have the KSA needs of each IG been assessed and documented?
Have appropriate requirements for communication, training and support been identified for each IG?
Have all activities to deliver these requirements been selected, costed and approved?
Have appropriate ways for measuring the results of these activities been identified?
Have all activities been assigned into project phases?
Have all assets and/or resources needed for the performance of these activities been created and/or assigned (if team members are global, consider time zone constraints)?
Have all mechanisms for delivery of activities (including third parties) been identified and made ready?
Have all activities (or at least those in upcoming phases) been scheduled as necessary?
Have all necessary communications occurred?
Have all necessary validations and approvals occurred?
Have all adoption barriers or challenges been addressed?
Have all potential risks been identified and plans for mitigation should they occurred been created?
Is there anything else that has not been done that needs to be done prior to project launch?
Are we ready to go?